## CRNS-CA_ADPQ_Prototype-Sprint_1
Issue Type | Issue key | Issue id | Parent id | Summary | Assignee | Reporter | Priority | Status | Resolution
Sub-task | CRNS-132 | 46731 | 45906 | [API] Get notifications specific to a user | shiva.dixit | shiva.dixit | Major | Done | Done
Sub-task | CRNS-118 | 46717 | 45906 | [API] Get current location of User: define API | shiva.dixit | shiva.dixit | Major | Done | Done
Sub-task | CRNS-117 | 46716 | 45906 | [API] Get profile location of User: define API | shiva.dixit | shiva.dixit | Major | Done | Done
Sub-task | CRNS-116 | 46715 | 45906 | [API] Get list of users: define API | shiva.dixit | shiva.dixit | Major | Done | Done
Sub-task | CRNS-115 | 46714 | 45906 | [API] Get user notification options: define API | shiva.dixit | shiva.dixit | Major | Done | Done
Sub-task | CRNS-109 | 46667 | 45906 | [API]: Check Email already registered - define API | shiva.dixit | shiva.dixit | Major | Done | Done
Sub-task | CRNS-108 | 46666 | 45906 | [API]: Check Unique User Name - define API | shiva.dixit | shiva.dixit | Major | Done | Done
Sub-task | CRNS-107 | 46662 | 46501 | [DEV]: Mock the REST APIs. | bincy.samuel | bincy.samuel | Major | In Progress
Sub-task | CRNS-87 | 46615 | 45806 | [DEV] Save User Device information at the time of User Login | shiva.dixit | shiva.dixit | Major | Done | Done
Sub-task | CRNS-86 | 46614 | 45806 | [DEV][API] Implement REST APIs for Login | shiva.dixit | shiva.dixit | Major | Done | Done
Task | CRNS-84 | 46602 |  | [Mobile][Dev] Create MOCK framework for server apis to support mobile app | harish.patidar | harish.patidar | Major | Done | Done
Task | CRNS-83 | 46525 |  | [DEV][Mobile] Add app icons and splash screens for iOS devices | harish.patidar | harish.patidar | Major | Done | Done
Task | CRNS-82 | 46502 |  | [DEV][UI] Make Web pages responsive | mohan.singh@intimetec.com | shiva.dixit | Major | Done | Done
Task | CRNS-81 | 46501 |  | [DEV][WEB] Setup Unit Testing framework | bincy.samuel | shiva.dixit | Major | To Do
Task | CRNS-80 | 46333 |  | [DEV][Mobile] User profile setup after login | harish.patidar | harish.patidar | Major | Done | Done
Task | CRNS-79 | 46321 |  | Create README Document | grace.arpana | grace.arpana | Major | In Progress
Task | CRNS-78 | 46125 |  | [DEV][Mobile] Forgot screen implementation | harish.patidar | harish.patidar | Major | Done | Done
Task | CRNS-77 | 46124 |  | [DEV][Mobile] Register screen implementation | harish.patidar | harish.patidar | Major | Done | Done
Task | CRNS-76 | 46123 |  | [DEV][Mobile] Login screen implementation | harish.patidar | harish.patidar | Major | Done | Done
Task | CRNS-75 | 46118 |  | [DEV][Mobile] Unit testing setup using Jasmine and Karma | sunil.jhamnani | harish.patidar | Major | Done | Done
Task | CRNS-74 | 46053 |  | [DEV][Mobile] Modularize the app structure. | harish.patidar | harish.patidar | Major | Done | Done
Sub-task | CRNS-73 | 46002 | 45906 | [API]: Update User Notification Options - define API | shiva.dixit | jitendra.sen | Major | Done | Done
Sub-task | CRNS-72 | 46000 | 45906 | [API]: get Notification detail - define API | shiva.dixit | jitendra.sen | Major | Done | Done
Sub-task | CRNS-71 | 45999 | 45906 | [API]: get Notifications list - define API | shiva.dixit | jitendra.sen | Major | Done | Done
Sub-task | CRNS-70 | 45998 | 45906 | [API]: get User profile - define API | shiva.dixit | jitendra.sen | Major | Done | Done
Sub-task | CRNS-69 | 45994 | 45906 | [API]: Logout - define API | shiva.dixit | jitendra.sen | Major | Done | Done
Sub-task | CRNS-68 | 45926 | 45924 | [CREATIVE] Layout design: APP | mohan.singh@intimetec.com | shiva.dixit | Major | Done | Done
Sub-task | CRNS-67 | 45925 | 45924 | [CREATIVE] Layout design: WEB | mohan.singh@intimetec.com | shiva.dixit | Major | Done | Done
Story | CRNS-66 | 45924 |  | Layout design | mohan.singh@intimetec.com | shiva.dixit | Major | Done | Done
Sub-task | CRNS-65 | 45923 | 45809 | [DEV] Generate swagger documents for REST APIs | bincy.samuel | shiva.dixit | Major | Done | Done
Sub-task | CRNS-64 | 45922 | 45809 | [DEV] Integrate Swagger in Web project | bincy.samuel | shiva.dixit | Major | Done | Done
Sub-task | CRNS-53 | 45911 | 45906 | [API]: Background User location update - define API | shiva.dixit | shiva.dixit | Major | Done | Done
Sub-task | CRNS-52 | 45910 | 45906 | [API]: Admin send notification - define API | shiva.dixit | shiva.dixit | Major | Done | Done
Sub-task | CRNS-51 | 45909 | 45906 | [API]: set User profile - define API | shiva.dixit | shiva.dixit | Major | Done | Done
Sub-task | CRNS-50 | 45908 | 45906 | [API]: User Registration - define API | shiva.dixit | shiva.dixit | Major | Done | Done
Sub-task | CRNS-49 | 45907 | 45906 | [API]: Login - define API | shiva.dixit | shiva.dixit | Major | Done | Done
Story | CRNS-48 | 45906 |  | Define REST APIs | harish.patidar | shiva.dixit | Major | Done | Done
Sub-task | CRNS-47 | 45905 | 45904 | [DEVOPS] Jenkins build setup and deployment |  | shiva.dixit | Major | To Do
Task | CRNS-46 | 45904 |  | Establish CI and CD infrastructure | umesh.mehta | shiva.dixit | Major | In Progress
Sub-task | CRNS-45 | 45903 | 45802 | [DEVOPS] Verify Docker image for AWS deployment | umesh.mehta | shiva.dixit | Major | Done | Done
Sub-task | CRNS-44 | 45902 | 45802 | [DEVOPS] Verify Docker image for Dev environment | umesh.mehta | shiva.dixit | Major | Done | Done
Sub-task | CRNS-43 | 45901 | 45802 | [DEVOPS] Create Docker image with specified technology stack | umesh.mehta | shiva.dixit | Major | Done | Done
Sub-task | CRNS-33 | 45834 | 45806 | [QA-WEB] Admin user Login | jitendra.sen | shiva.dixit | Major | To Do
Sub-task | CRNS-17 | 45818 | 45806 | [CREATIVE]: Design Login Screen | mohan.singh@intimetec.com | shiva.dixit | Major | Done | Done
Task | CRNS-16 | 45817 |  | Create Database design and finalize schema structure | shiva.dixit | shiva.dixit | Major | Done | Done
Sub-task | CRNS-14 | 45815 | 45806 | [WEB] Admin: Login Unit Test | bincy.samuel | shiva.dixit | Major | To Do
Sub-task | CRNS-12 | 45813 | 45806 | [WEB] Admin: Login | bincy.samuel | shiva.dixit | Major | Done | Done
Story | CRNS-8 | 45809 |  | Integrate Swagger Document in Project | bincy.samuel | shiva.dixit | Major | Done | Done
Story | CRNS-5 | 45806 |  | User Login and Admin(Dummy) account Setup | bincy.samuel | shiva.dixit | Major | To Do
Task | CRNS-4 | 45805 |  | Integrate Java and Mobile App Project | shiva.dixit | shiva.dixit | Major | Done | Done
Task | CRNS-3 | 45804 |  | Setup Project for Mobile App | harish.patidar | shiva.dixit | Major | Done | Done
Task | CRNS-2 | 45803 |  | Setup Java Project | bincy.samuel | shiva.dixit | Major | Done | Done
Story | CRNS-1 | 45802 |  | Setup Docker | deepak.sharma | shiva.dixit | Major | To Do