## CRNS-CA_ADPQ_Prototype-Sprint_2
Issue Type | Issue key | Issue id | Parent id | Summary | Assignee | Reporter | Priority | Status | Resolution
Sub-task | CRNS-136 | 46735 | 46634 | [WEB] Implement notifications details/view | sunil.jhamnani | shiva.dixit | Major | To Do
Sub-task | CRNS-135 | 46734 | 46634 | [WEB] Implement notifications list | sunil.jhamnani | shiva.dixit | Major | To Do
Sub-task | CRNS-134 | 46733 | 46634 | [WEB] Implement Send notifications | sunil.jhamnani | shiva.dixit | Major | To Do
Sub-task | CRNS-133 | 46732 | 46635 | [DEV][API] Get user specific notifications: implement API | shiva.dixit | shiva.dixit | Major | Done | Done
Sub-task | CRNS-132 | 46731 | 45906 | [API] Get notifications specific to a user | shiva.dixit | shiva.dixit | Major | Done | Done
Sub-task | CRNS-131 | 46730 | 45807 | [DEV][Mobile] Setup account screen integrate with Server API | harish.patidar | harish.patidar | Major | In Progress
Sub-task | CRNS-130 | 46729 | 45807 | [WEB] Integrate Google API for location | sunil.jhamnani | shiva.dixit | Major | Done | Done
Sub-task | CRNS-129 | 46728 | 45807 | [WEB] Implement User Profile Update | sunil.jhamnani | shiva.dixit | Major | To Do
Sub-task | CRNS-128 | 46727 | 45807 | [WEB] Implement User Profile View | sunil.jhamnani | shiva.dixit | Major | Done | Done
Sub-task | CRNS-127 | 46726 | 45807 | [WEB] Implement User Registration | sunil.jhamnani | shiva.dixit | Major | Done | Done
Sub-task | CRNS-126 | 46725 | 46634 | [DEV][API] Send notification from Admin Panel: Implement API | shiva.dixit | shiva.dixit | Major | Done | Done
Sub-task | CRNS-125 | 46724 | 46634 | [DEV][API] Get notification details by for Admin login: Implement API | shiva.dixit | shiva.dixit | Major | Done | Done
Sub-task | CRNS-124 | 46723 | 46634 | [DEV][API] Get notification list for Admin login: Implement API | shiva.dixit | shiva.dixit | Major | Done | Done
Task | CRNS-123 | 46722 |  | [DEV][Mobile] Side Menu UI implemeentation | harish.patidar | harish.patidar | Major | Done | Done
Task | CRNS-122 | 46721 |  | [DEV][Mobile] Need to add Push Plugin and Implementation | harish.patidar | harish.patidar | Major | Done | Done
Sub-task | CRNS-120 | 46719 | 45807 | [DEV][API] Get profile location and current location of User: implement API | shiva.dixit | shiva.dixit | Major | Done | Done
Sub-task | CRNS-118 | 46717 | 45906 | [API] Get current location of User: define API | shiva.dixit | shiva.dixit | Major | Done | Done
Sub-task | CRNS-117 | 46716 | 45906 | [API] Get profile location of User: define API | shiva.dixit | shiva.dixit | Major | Done | Done
Sub-task | CRNS-116 | 46715 | 45906 | [API] Get list of users: define API | shiva.dixit | shiva.dixit | Major | Done | Done
Sub-task | CRNS-115 | 46714 | 45906 | [API] Get user notification options: define API | shiva.dixit | shiva.dixit | Major | Done | Done
Task | CRNS-114 | 46713 |  | [DEV][Mobile] Settings screen implementation | harish.patidar | harish.patidar | Major | Done | Done
Task | CRNS-112 | 46707 |  | [DEV][Mobile] Need to integrate setup account screen with MOCK data | harish.patidar | harish.patidar | Major | Done | Done
Sub-task | CRNS-111 | 46669 | 45807 | [DEV][API] Implement REST API for Email already registered check (/users/isEmailRegistered) | shiva.dixit | shiva.dixit | Major | Done | Done
Sub-task | CRNS-110 | 46668 | 45807 | [DEV][API] Implement REST API for Unique username check (/users/isUniqueUsername) | shiva.dixit | shiva.dixit | Major | Done | Done
Sub-task | CRNS-109 | 46667 | 45906 | [API]: Check Email already registered - define API | shiva.dixit | shiva.dixit | Major | Done | Done
Sub-task | CRNS-108 | 46666 | 45906 | [API]: Check Unique User Name - define API | shiva.dixit | shiva.dixit | Major | Done | Done
Sub-task | CRNS-107 | 46662 | 46501 | [DEV]: Mock the REST APIs. | bincy.samuel | bincy.samuel | Major | In Progress
Story | CRNS-106 | 46635 |  | [APP] Receive and view notification |  | shiva.dixit | Major | To Do
Story | CRNS-105 | 46634 |  | [WEB] Publish and View notifications | shiva.dixit | shiva.dixit | Major | To Do
Sub-task | CRNS-101 | 46630 | 45807 | [DEV][API] Implement get user list API (/user/list) | shiva.dixit | shiva.dixit | Major | Done | Done
Sub-task | CRNS-100 | 46629 | 45807 | [DEV][API] Implement User update location API (/user/updateLocation) | shiva.dixit | shiva.dixit | Major | Done | Done
Sub-task | CRNS-99 | 46628 | 45807 | [DEV][API] Implement User update notification settings API (/user/setNotificationOptions) | shiva.dixit | shiva.dixit | Major | Done | Done
Sub-task | CRNS-98 | 46627 | 45807 | [DEV][API] Implement User get notification settings API (/user/getNotificationOptions) | shiva.dixit | shiva.dixit | Major | Done | Done
Sub-task | CRNS-97 | 46625 | 45807 | [DEV][API] Implement User set account API (/user/setupAccount) | shiva.dixit | shiva.dixit | Major | Done | Done
Sub-task | CRNS-96 | 46624 | 45807 | [DEV][API] Implement User set profile API (/user/setProfile) | shiva.dixit | shiva.dixit | Major | Done | Done
Sub-task | CRNS-95 | 46623 | 45807 | [DEV][API] Implement User get profile Rest API (/user/getProfile) | shiva.dixit | shiva.dixit | Major | Done | Done
Sub-task | CRNS-94 | 46622 | 45807 | [DEV][API] Implement User Registeration Rest API | shiva.dixit | shiva.dixit | Major | Done | Done
Sub-task | CRNS-93 | 46621 | 45807 | [DEV][Mobile] Login and Register API integration | harish.patidar | shiva.dixit | Major | Done | Done
Story | CRNS-92 | 46620 |  | [WEB] User Registration and Manage Profile (Both Admin and User) | sunil.jhamnani | shiva.dixit | Major | In Progress
Story | CRNS-90 | 46618 |  | [WEB] User Login | sunil.jhamnani | shiva.dixit | Major | In Progress
Sub-task | CRNS-87 | 46615 | 45806 | [DEV] Save User Device information at the time of User Login | shiva.dixit | shiva.dixit | Major | Done | Done
Sub-task | CRNS-86 | 46614 | 45806 | [DEV][API] Implement REST APIs for Login | shiva.dixit | shiva.dixit | Major | Done | Done
Task | CRNS-84 | 46602 |  | [Mobile][Dev] Create MOCK framework for server apis to support mobile app | harish.patidar | harish.patidar | Major | Done | Done
Task | CRNS-82 | 46502 |  | [DEV][UI] Make Web pages responsive | mohan.singh@intimetec.com | shiva.dixit | Major | Done | Done
Task | CRNS-81 | 46501 |  | [DEV][WEB] Setup Unit Testing framework | bincy.samuel | shiva.dixit | Major | To Do
Task | CRNS-79 | 46321 |  | Create README Document | grace.arpana | grace.arpana | Major | In Progress
Sub-task | CRNS-73 | 46002 | 45906 | [API]: Update User Notification Options - define API | shiva.dixit | jitendra.sen | Major | Done | Done
Sub-task | CRNS-72 | 46000 | 45906 | [API]: get Notification detail - define API | shiva.dixit | jitendra.sen | Major | Done | Done
Sub-task | CRNS-71 | 45999 | 45906 | [API]: get Notifications list - define API | shiva.dixit | jitendra.sen | Major | Done | Done
Sub-task | CRNS-70 | 45998 | 45906 | [API]: get User profile - define API | shiva.dixit | jitendra.sen | Major | Done | Done
Sub-task | CRNS-69 | 45994 | 45906 | [API]: Logout - define API | shiva.dixit | jitendra.sen | Major | Done | Done
Sub-task | CRNS-65 | 45923 | 45809 | [DEV] Generate swagger documents for REST APIs | bincy.samuel | shiva.dixit | Major | Done | Done
Sub-task | CRNS-64 | 45922 | 45809 | [DEV] Integrate Swagger in Web project | bincy.samuel | shiva.dixit | Major | Done | Done
Sub-task | CRNS-53 | 45911 | 45906 | [API]: Background User location update - define API | shiva.dixit | shiva.dixit | Major | Done | Done
Sub-task | CRNS-52 | 45910 | 45906 | [API]: Admin send notification - define API | shiva.dixit | shiva.dixit | Major | Done | Done
Sub-task | CRNS-51 | 45909 | 45906 | [API]: set User profile - define API | shiva.dixit | shiva.dixit | Major | Done | Done
Sub-task | CRNS-50 | 45908 | 45906 | [API]: User Registration - define API | shiva.dixit | shiva.dixit | Major | Done | Done
Sub-task | CRNS-49 | 45907 | 45906 | [API]: Login - define API | shiva.dixit | shiva.dixit | Major | Done | Done
Story | CRNS-48 | 45906 |  | Define REST APIs | harish.patidar | shiva.dixit | Major | Done | Done
Sub-task | CRNS-47 | 45905 | 45904 | [DEVOPS] Jenkins build setup and deployment |  | shiva.dixit | Major | To Do
Task | CRNS-46 | 45904 |  | Establish CI and CD infrastructure | umesh.mehta | shiva.dixit | Major | In Progress
Sub-task | CRNS-45 | 45903 | 45802 | [DEVOPS] Verify Docker image for AWS deployment | umesh.mehta | shiva.dixit | Major | In Progress
Sub-task | CRNS-44 | 45902 | 45802 | [DEVOPS] Verify Docker image for Dev environment | umesh.mehta | shiva.dixit | Major | Done | Done
Sub-task | CRNS-43 | 45901 | 45802 | [DEVOPS] Create Docker image with specified technology stack | umesh.mehta | shiva.dixit | Major | Done | Done
Sub-task | CRNS-42 | 45843 | 46635 | [QA-APP] Verification of notification received |  | shiva.dixit | Major | To Do
Sub-task | CRNS-41 | 45842 | 46634 | [QA-WEB] Send Notification |  | shiva.dixit | Major | To Do
Sub-task | CRNS-40 | 45841 | 46635 | [APP] Notification details: Unit Test cases |  | shiva.dixit | Major | To Do
Sub-task | CRNS-38 | 45839 | 46635 | [APP] Notification details: Implementation |  | shiva.dixit | Major | To Do
Sub-task | CRNS-36 | 45837 | 46635 | [CREATIVE]: Design notification detail view | mohan.singh@intimetec.com | shiva.dixit | Major | Done | Done
Sub-task | CRNS-35 | 45836 | 46634 | [CREATIVE]: Design Admin send notification screen | mohan.singh@intimetec.com | shiva.dixit | Major | Done | Done
Sub-task | CRNS-33 | 45834 | 45806 | [QA-WEB] Admin user Login | jitendra.sen | shiva.dixit | Major | To Do
Sub-task | CRNS-32 | 45833 | 45807 | [QA-APP] User manage profile |  | shiva.dixit | Major | To Do
Sub-task | CRNS-31 | 45832 | 46618 | [QA-WEB] User manage profile |  | shiva.dixit | Major | To Do
Sub-task | CRNS-30 | 45831 | 45807 | [QA-APP] User Login |  | shiva.dixit | Major | To Do
Sub-task | CRNS-29 | 45830 | 46618 | [QA-WEB] User Login |  | shiva.dixit | Major | To Do
Sub-task | CRNS-28 | 45829 | 46618 | [QA-WEB] User Registration |  | shiva.dixit | Major | To Do
Sub-task | CRNS-27 | 45828 | 45807 | [APP] User manage profile: Unit Test cases | harish.patidar | shiva.dixit | Major | To Do
Sub-task | CRNS-26 | 45827 | 46618 | [WEB] User manage profile: Unit Test cases |  | shiva.dixit | Major | To Do
Sub-task | CRNS-25 | 45826 | 46618 | [WEB] User Resgistration: Unit Test cases |  | shiva.dixit | Major | To Do
Sub-task | CRNS-24 | 45825 | 45807 | [APP] User manage profile: implementation | harish.patidar | shiva.dixit | Major | To Do
Sub-task | CRNS-23 | 45824 | 46618 | [WEB] User manage profile: implementation | sunil.jhamnani | shiva.dixit | Major | Done | Done
Sub-task | CRNS-22 | 45823 | 45807 | [APP] User: Login implementation | harish.patidar | shiva.dixit | Major | Done | Done
Sub-task | CRNS-21 | 45822 | 46618 | [WEB] User: Login implementation | sunil.jhamnani | shiva.dixit | Major | Done | Done
Sub-task | CRNS-20 | 45821 | 46618 | [WEB] User Registration: Implementation | sunil.jhamnani | shiva.dixit | Major | Done | Done
Sub-task | CRNS-19 | 45820 | 45807 | [CREATIVE]: Design User Manage Profile page | mohan.singh@intimetec.com | shiva.dixit | Major | Done | Done
Sub-task | CRNS-18 | 45819 | 45807 | [CREATIVE]: Design User registration form | mohan.singh@intimetec.com | shiva.dixit | Major | Done | Done
Sub-task | CRNS-17 | 45818 | 45806 | [CREATIVE]: Design Login Screen | mohan.singh@intimetec.com | shiva.dixit | Major | Done | Done
Task | CRNS-16 | 45817 |  | Create Database design and finalize schema structure | shiva.dixit | shiva.dixit | Major | Done | Done
Sub-task | CRNS-14 | 45815 | 45806 | [WEB] Admin: Login Unit Test | bincy.samuel | shiva.dixit | Major | To Do
Sub-task | CRNS-12 | 45813 | 45806 | [WEB] Admin: Login | bincy.samuel | shiva.dixit | Major | Done | Done
Sub-task | CRNS-11 | 45812 | 46620 | [WEB] Admin: User Creation | shiva.dixit | shiva.dixit | Major | To Do
Story | CRNS-8 | 45809 |  | Integrate Swagger Document in Project | bincy.samuel | shiva.dixit | Major | Done | Done
Story | CRNS-6 | 45807 |  | User registration & manage profile | shiva.dixit | shiva.dixit | Major | To Do
Story | CRNS-5 | 45806 |  | User Login and Admin(Dummy) account Setup | bincy.samuel | shiva.dixit | Major | To Do
Story | CRNS-1 | 45802 |  | Setup Docker | deepak.sharma | shiva.dixit | Major | To Do